STAGE 4 — PLANNING PHASE

Project Execution Strategy

Team Structure

Developer 1 (You)

Primary Ownership:

Frontend
UI/UX
Dashboard
Asset Management
Reports
Testing

Secondary:

Backend APIs
Database Review

Developer 2 (Friend)

Primary Ownership:

Python Monitoring Agent
FastAPI Monitoring Service
Change Detection
Heartbeat Engine
Agent Packaging

Secondary:

Backend APIs
Database Review

Timeline Analysis

Total Duration

8 Weeks

Constraint

Semester Exams until June 16

This means:

Week 1

Reduced productivity.

Weeks 2-8

Full development pace.

Critical Path Analysis

The entire project depends on these items:

Authentication
↓
Organization Structure
↓
Asset Management
↓
Monitoring Agent
↓
Snapshot Processing
↓
Change Detection
↓
Alerts
↓
Reports

If Monitoring Agent slips,
the entire product value drops significantly.

Therefore:

Monitoring Agent =Priority #1

Final MVP Definition

Must work by release:

Core Platform

- Authentication

- Multi-company structure

- Branch management

- Department management

- Employee management

Asset Management

- Asset CRUD

- Assignment

- Transfer

- Return

- Disposal

Monitoring

- Device registration

- Hardware collection

- Software collection

- Heartbeat

- Snapshot upload

Security

- Change detection

- Risk classification

- Alert generation

Operations

- Ticketing

- Approval workflow

Governance

- Audit logs

- Reports

Maintenance

- Vendor management

- Warranty tracking

- AMC tracking

Sprint Roadmap

Sprint 0

Duration:

3 Days

Goal:

Foundation Setup

Tasks:

- Git repository

- Project structure

- Coding standards

- Supabase project

- Environment setup

- Authentication setup

Deliverable:

Login Working
Project Running

Sprint 1

Duration:

Week 1

Goal:

Organization Foundation

Modules:

- Company

- Branch

- Department

- Employee

Frontend:

- Layout

- Sidebar

- Navbar

Backend:

- CRUD APIs

Deliverable:

Organization Management Complete

Sprint 2

Duration:

Week 2

Goal:

Asset Management Core

Modules:

- Asset CRUD

- Categories

- Asset Images

- Assignment

Deliverable:

Asset Inventory Working

Sprint 3

Duration:

Week 3

Goal:

Monitoring Agent MVP

Agent:

- Registration

- Authentication

- Snapshot Upload

Backend:

- Agent APIs

Database:

- Monitoring tables

Deliverable:

Device Successfully Registered

Sprint 4

Duration:

Week 4

Goal:

Change Detection Engine

Modules:

- Snapshot Comparison

- Event Generation

- Alert Generation

Deliverable:

Hardware Changes Detected

Sprint 5

Duration:

Week 5

Goal:

Ticketing + Approvals

Modules:

- Tickets

- Approval Engine

Deliverable:

Request Workflow Working

Sprint 6

Duration:

Week 6

Goal:

Maintenance Management

Modules:

- Vendors

- Warranty

- AMC

Deliverable:

Maintenance Tracking Working

Sprint 7

Duration:

Week 7

Goal:

Reports + Audit Logs

Modules:

- Audit Trail

- Asset Reports

- Security Reports

Deliverable:

Governance Features Complete

Sprint 8

Duration:

Week 8

Goal:

Stabilization

Tasks:

- Bug fixing

- Security review

- Performance review

- UAT

Deliverable:

Release Candidate

Repository Structure

Approved:

ITAMS/

├── frontend/

├── backend-express/

├── monitoring-service/

├── agent/

├── docs/

├── database/

└── deployment/

Major Risks

Risk 1

Monitoring Agent Complexity

Impact:

Very High

Mitigation:

Build by milestones:

Collect
↓
Upload
↓
Register
↓
Heartbeat
↓
Compare

Never attempt everything at once.

Risk 2

Overbuilding Dashboard

Impact:

Medium

Mitigation:

Functional first.
Visual polish later.

Risk 3

Database Redesign

Impact:

High

Mitigation: Complete Stage 5 Database Design before coding.

AI Development Strategy

Use Anti-Gravity AI For

- Full feature implementation

- Refactoring

- UI generation

- API generation

Use Codex For

- Bug fixing

- Database queries

- Small features

- Validation